## Start
[7 empty] | Project Manager: Nguyen Van Hau |  | Project Name: Job hunter | [11 empty] | Report Date: 15/3/2026
Project Objective: Build Job hunter
Sub-Objectives | [7 empty] | Major Tasks |  | Schedule | [9 empty] | Owners and Helpers
l | l | l | l | l | l | l | 1 | Requirement Analysis & SRS |  | m | [9 empty] | A
[7 empty] | 2 | System Design (Use Case, ERD) |  | m | [9 empty] | A
[7 empty] | 3 | Database Implementation | [11 empty] | A
[7 empty] | 4 | Project Setup (Spring MVC + JPA) | [11 empty] | A
m | m | [5 empty] | 5 | User Registration Function (UI + Backend + Integration + Testing) | [11 empty] | A | A
m | m | [5 empty] | 6 | User Authentication (Login/Logout) Function | [11 empty] | A | A
m | [6 empty] | 7 | User Profile Management Function | [11 empty] | A | A
m | [6 empty] | 8 | Password Recovery Function
|  | m |  |  |  |  | 9 | Job Listing Function (View Job List)
|  | m |  |  |  |  | 10 | Job Search Function
|  | m |  |  |  |  | 11 | Job Detail Viewing Function
|  | m |  |  |  |  | 12 | Job Application Function (Core Feature)
m |  | m |  |  |  |  | 13 | Applied Jobs Management Function
[5 empty] | m |  | 14 | Company Listing Function
[5 empty] | m |  | 15 | Company Detail Viewing Function
[6 empty] | m | 16 | Admin User Management Function
[6 empty] | m | 17 | Admin Job Management Function
[6 empty] | m | 18 | Admin Company Management Function
[6 empty] | m | 19 | Admin Application Management Function
[7 empty] | 20 | 16. UI Development & Integration (Bootstrap + Thymeleaf)
[7 empty] | 21 | 17. System Testing & Bug Fixing
[7 empty] | 22 | 18. Deployment & Documentation
23
24
[8 empty] | Risks, Qualitatives, Other Metrics | [5 empty] | Green=Adequate, Yellow=Worrisome, Red=Dangerous | [5 empty] | Haunv
[7 empty] | 1 | 1. Thiếu thời gian → Ưu tiên core feature (Apply Job)
[7 empty] | 2 | 2. Lỗi logic backend → Test từng use case
[7 empty] | 3 | 3. UI không đồng nhất → Dùng Bootstrap template
4
5
[9 empty] | # Internal People assigned to the project: | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4. Job Search & Viewing Module
1. User Management Module | 2. Authentication Module | 3. Job Management Module |  | 5. Job Application Module (Core) | 6. Company Module | 7. Admin Module |  |  |  | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | Dev 1 | Tester
Millions
[22 empty] | Labels | Budgeted | Expended
User Management
Role Management
Login Function
[12 empty] | m | l | q | n |  | A | Primary Owner
[11 empty] | Wingdings | m | l | q | n |  | B | Secondary Owner
[17 empty] | C | Tertiary Owner
Adequate
Worrisome
Dangerous
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics
Major Tasks
and Risks
Note on O79: Microsoft Office User: Đánh vào m ¦ l ¦ q